## Activity Plan
Activity Plan
[6 empty] | Date： | DD/MM/YYYY
By：
Program Name: Sound Mind, Sound Body Program
Vision:Sound Mind Sound Body Through Sport
Program Plan | [5 empty] | Fiscal Year 2027 |  |  |  | Fiscal Year 2028 |  |  | Fiscal Year 2029
Program Objectives | Annual Objectives | To achieve annual objectives⇒ | Main Activities | KPI | Means of Verification | 1st Quarter January-March | 2nd Quarter April-June | 3rd Quarter July- September | 4th Quarter October-December | Annual Objectives | 1st half January-June | Second half July-December | Annua Objectiveas | 1st half January-June | Second half July-December
| FY27 |  |  |  |  | ( major events, annual activities, or milestones here, if applicable.) | ( major events, annual activities, or milestones here, if applicable.) | ( major events, annual activities, or milestones here, if applicable.) | ( major events, annual activities, or milestones here, if applicable.) | FY28 | ( major events, annual activities, or milestones here, if applicable.) | ( major events, annual activities, or milestones here, if applicable.) | FY29 | ( major events, annual activities, or milestones here, if applicable.) | ( major events, annual activities, or milestones here, if applicable.)
Objective-1 | Annual Objectives- 1-1 |  | Main Activity 1 to achieve Annual Objective(s) | KPI | Means of Verification
| Annual Objectives- 1-2 |  | Main Activity 2 to achieve Annual Objective(s) | KPI | Means of Verification
| Annual Objectives- 1-3 |  | Main Activity 3 to achieve Annual Objective(s) | KPI | Means of Verification
Objective-2 | Annual Objectives- 2-1 | To achieve annual objectives⇒ | Main Activity 1 to achieve Annual Objective(s) | KPI | Means of Verification
| Annual Objectives- 2-2 |  | Main Activity 2 to achieve Annual Objective(s) | KPI | Means of Verification
| Annual Objectives- 2-3 |  | Main Activity 3 to achieve Annual Objective(s) | KPI | Means of Verification
Objective-3 | Annual Objectives- 3-1 | To achieve annual objectives⇒ | Main Activity 1 to achieve Annual Objective(s) | KPI | Means of Verification
| Annual Objectives- 3-2 |  | Main Activity 2 to achieve Annual Objective(s) | KPI | Means of Verification
| Annual Objectives- 3-3 |  | Main Activity 3 to achieve Annual Objective(s) | KPI | Means of Verification
Note on C12: If there is only one Annual Objective for this year, no need to fill out "Annual Objectives 1-2", nither "1-3"
Note on E13: If you set only "Annual Objectives 1-1", you can still set several "Main Activities" to achieve "Program Objecrtive-1".

## Example
Activity Plan
[6 empty] | Date： | 01/03/2026
[6 empty] | By： | Tigar Onitsuka
Program Name: Sound Mind, Sound Body Program
Vision: Sound Mind. Sound Body. Through Sport.
Program Plan | [5 empty] | Fiscal Year 2027 |  |  |  | Fiscal Year 2028 |  |  | Fiscal Year 2029
Program Objectives | Annual Objectives | To achieve annual objectives⇒ | Main Activities | KPI | Means of Verification | 1st Quarter January-March | 2nd Quarter April-June | 3rd Quarter July- September | 4th Quarter October-December | Annual Objectives | 1st half January-June | Second half July-December | Annua Objectiveas | 1st half January-June | Second half July-December
| FY27 |  |  |  |  | Sports Day/Parents Day/Sports test | Coaching Workshop/Leadership mindset session | Coaching Workshops/Para Sports Event | Sports test/Para Sports Event | FY28 | Sports test/Coaching workshops/mental health seminar/Para sports event | Sports test/Coaching workshops/mental health webinar/Holiday training session | FY29 | Sports test/Coaching workshops/mental health seminar/Para sports event | Sports test/Coaching workshops/mental health webinar
1 Ensure regular opportunities for individuals with disabilities to engage in physical activity, thereby improving their quality of life | 1-1 To ensure opportunities for inclusive sports that everyone can easily access and enjoy. |  | 1-1-1 Conducting club trial sessions (Table Tennis, Athletics, Badmington, Boccia, Floorball, Goalball Sapporo（at the main activitiy location) Once a month for each sport Aim for 20-30 people each time | 1-1-1 Increase in number of participants Increase in repeat participants | Number of Participants Participation Rate Attendee Data | ・ Conducting club trial sessions once per month for all six sports | ・ Conducting club trial sessions once per month for all six sports | ・ Conducting club trial sessions once per month for all six sports ・ Special summer event with parents will be conducted two times during the summer vacation | ・ Conducting club trial sessions once per month for all six sports in October ＆ November ・ Special Christmas event with parents will be conducted once in December | To ensure opportunities for inclusive sports that everyone can easily access and enjoy. | ・ Conducting club trial sessions once per month for all six sports ・ Special summer event with parents will be conducted two times during the summer vacation | ・ Conducting club trial sessions once per month for all six sports in October ＆November ・ Special Christmas event with parents will be conducted once in December | To ensure opportunities for inclusive sports that everyone can easily access and enjoy. | ・ Conducting club trial sessions once per month for all six sports ・ Special summer event with parents will be conducted two times during the summer vacation ・ Expanding nationwide as a model case | ・ Conducting club trial sessions once per month for all six sports in October ＆November ・ Special Christmas event with parents will be conducted once in December ・ Expanding nationwide as a model case
|  |  | 1-1-2 Utilize the club membership system to promote and expand community building Provide opportunities for people with and without disabilities to connect and become friends Once a month in Sapporo | 1-1-2 Shift the local residents' awareness through networking events and community-wide activities. | Interviews Pre- and post-activity surveys | ・ Conducting the club membership event once per month for every month ・ Collect pre-survey data | ・ Conducting the club membership event once per month for every month | ・ Conducting the club membership event once per month for every month ・ Interview with members | ・ Conducting the club membership event once per month for October & November ・ Collect post-survey data |  | ・ Conducting the club membership event once per month for every month ・ Collect pre-survey data | ・ Conducting the club membership event once per month for every month ・ Collect post-survey data |  | ・ Conducting the club membership event once per month for every month ・ Collect pre-survey data | ・ Conducting the club membership event once per month for every month ・ Collect post-surveys
|  |  |  | 1-1-２ Enhancing self-esteem and perceived physical competence through the use of portfolios | Monitoring Interviews Video Observation | ・ Conducting Sports Test in March ・ Interviewing and observing the participants | ・ Setting the task ・ Introduction to training for solving the task | ・ Setting the task ・ Continuous training for solving the task | ・ Conducting sports test in November ・ Interviewing and observing the participants |  | ・ Condacting Sports Pre-Test in April | ・ Conducting Sports Post-Test in November |  | ・ Condacting Sports Pre-Test in April | ・ Condacting Sports Post-Test in Nov
2 Promote the development of instructors and leaders who support individuals with disabilities | 2-1 Increrase number of volunteers | To achieve annual objectives⇒ | 2-1 Strategize on recruiting volunteers during the club trial sessions (Para Sports and joint programs with individuals with disabilities) @ Sapporo Once a month for each sport Aim for 10-15 people each time | 2-1 Increase in the number of volunteers Securing a stable number of volunteers | Number of Participants Participation Rate Attendee Data | ・ Publicizing volunteer cooperation when holding club trial sessions ・ Requesting cooperation from, and publicizing activities to, local organizations ・ Expanding publicity efforts to local universities and other educational institutions | ・ Publicizing volunteer cooperation when holding club trial sessions ・ Requesting cooperation from, and publicizing activities to, local organizations ・ Expanding publicity efforts to local universities and other educational institutions | ・ Publicizing volunteer cooperation when holding club trial sessions ・ Requesting cooperation from, and publicizing activities to, local organizations ・ Expanding publicity efforts to local universities and other educational institutions ・ Holding exchange events between people with disabilities and non‑disabled people: three times during the summer period | ・ Dispatching volunteers to the prefectural sports tournament ・ Recruiting volunteers who have experience in international comprehensive games | Maintaining and continuing the number of volunteers | ・ Build-up the volunteering community using social media services effectively | ・ Accumulation of volunteer practice cases related to major sports events | Increase the number of volunteers | ・ Build-up the volunteering community, using social media service effectively | ・ Organizing regional volunteer events for/by volunteers
| 2-2 Conduct instructor training seminars |  | 2-2 Hold coaching workshops in collaboration with local parasport organizations and associations Three times a year in Sapporo, Obihiro and Asahikawa About 50 people | 2-2 Development of human resources supporting Para Sports | Number of Participants Participation Rate Attendee Data Survey |  | ・ Coaching workshops @ Sapporo in May | ・ Coaching Workshops @ Obihiro in July ・ Coaching Workshops @ Asahikawa in August ・ Collect surveys |  | Increase the number of instructor training seminars conducted | ・ Coaching Workshops in May | ・ Coaching Workshops in November | Shift the conduct of instructor training seminars to the local community | ・ Coaching Workshops in July | ・ Coaching Workshops in November
| 2-3 Support individuals in obtaining the beginner's Para Sports instructor qualification |  | 2-3 Implementing projects in collaboration with Sapporo University Twice a year in Sapporo About 20 people | 2-3 Fostering and strengthening a leadership mindset | Number of people passing certification Number of Para Sports events in Hokkaido Interviews Monitoring | ・ Conducting Sapporo University's Lecture meeting in March | ・ Conducting Leadership Mindset session in May | ・ Para Sports event in September ・ Collecting interviews from examinee | ・ Para Sports event in September ・ Collecting interviews from examinee | Support individuals in obtaining the beginner's Para Sports instructor qualification | ・ Para Sports event in June | ・ Holding a training session to improve instructional skills for obtaining the Para Sports Instructor certification (intermediate or advanced level) | Raise the certificate level of Para Sports Instructor qualifications to either the intermediate or advanced level | ・ Para Sports event in June | ・ Examination of the next-generation nurturing plan by acquirers and passers
3 To promote the improvement of mental health for all people, both with and without disabilities. | 3-1 To foster an understanding of the importance of mental health in contemporary society | To achieve annual objectives⇒ | 3-1 Delivery of off-campus classes in partnership with universities Three times a year in Sapporo, Obihiro and Asahikawa Apprrox. 50 people Primary target will be parents | 3-1 Committed to understanding and improving mental health and well-being | Pre- and post-activity survey Report submission | ・ Holding Parents' Day in February ・ Collect pre-survey data | ・ Delivery of off-campus classes in Sapporo in May | ・ Delivery of off-campus classes in Obihiro in July ・ Delivery of off-campus classes in Asahikawa in August | ・ Collect post-survery data ・ Analyze reports based on data collected from university students | Conduct practical mental health workshops | ・ Conducting mental health webinar two times in two regions | ・ Conducting mental health webinar two times in two regions | Conduct practical mental health workshops | ・ Conducting mental health seminar two times in two regions | ・ Conducting mental health webinar two times in two regions
| 3-2 Develop radio calisthenics that can be performed together by people with disabilities and non‑disabled individuals |  | 3-2 Development and implementation of an inclusive radio calisthenics committee Once a month in Sapporo about 10 people | 3-2-1 Developing and implementing inclusive radio calisthenics | Developing radio calisthenics Data on mental health | ・ Establishing an inclusive radio calisthenics committee ・ Conducting the meeting every month | ・ Developing a draft of radio calisthenics ・ Conducting the meeting every month | ・ Implementing inclusive radio calisthenics among the community ・ Conducting the meeting every month ・ Delivering mental health check | ・ Developing and implementing inclusive radio calisthenics ・ Conducting the meeting every month | Root the "Inclusive Radio Calisthenics" program in the local community | ・ Introducing "Inclusive Radio Calisthenics" to public schools ・ Conducting meetings every month | ・ Introducing "Inclusive radio Calisthenics" to the local schools ・ Conducting the meeting every month | Expand and promote the "Inclusive Radio Calisthenics" initiative nationwide/regionally | ・ Introducing "Inclusive radio Calisthenics" to the public schools ・ Conducting the meeting every month ・Collaborating with stakeholders to promote ”Inclusive Radio Calisthenics” | ・ Introducing "Inclusive Radio Calisthenics" to local schools ・ Conducting monthly meetings ・ Operating caravans for public-relations activities
|  |  |  | 3-2-2 Enhancing health awareness among local residents and fostering cooperation and community bonds | Number of Participants Questionnaire Monitoring Video Observation |  |  | ・ Monitoring in Septmber ・ Video Observation in September | ・ Collecting the survey in November | Improving health awareness and healthy daily habits |  | ・ Monitoring in September ・ Video Observation in September ・ Collecting the survey in November | Improving health awareness and healthy daily habits |  | ・ Monitoring in September ・ Video Observation in September ・ Collecting the survey in November
If there is on ly one annual objective, you may still set 1～3 main activities to achieve the goal.
If there is only one Annual Objective for this year, no need to fill out "Annual Objectives 1-2", nither "1-3"
Following up the previous year, you may revise annual objectives for FY28.
Following up the previous year, you may revise annual objectives for FY29.